## Gantt Import
Title | FLOC | Task Name | WO | Area | Shift | Discipline | Planned Hours | Actual Hours | Percent Complete | Status | Notes | Delay Reason | Updated By | Assigned Workers | Planned Start | Planned Finish | Actual Start | Actual Finish | Picture
4074701 | 120-122-SC-005 | SC-005 Replace Feedbox End Beam Pre | 4074701 | 120-122 | Day | Fitter | 110 |  | 0 | Not Started |  |  |  |  | 2026-04-21 06:00 | 2026-04-25 20:00
4053126 | 120-123-ML-001 | Prepare/build up Spare Trommel | 4053126 | 120-123 | Day | Fitter | 24 |  | 0 | Not Started |  |  |  |  | 2026-04-21 06:00 | 2026-04-22 06:00
4077484 | 120-121-CV-001 | 8W Mech OFF Insp Rollers 121-CV-001 | 4077484 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 09:15
4077486 | 120-121-CV-001 | 8W Mech OFF Insp Skirts 121-CV-001 | 4077486 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 14:15
4077483 | 120-121-CV-001 | 8W Mech OFF Insp Conv 121-CV-001 | 4077483 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 07:15
4071134 | 120-121-FE-003 | 24W Mech OFF Reline Feeder FE-003 | 4071134 | 120-121 | Day | Fitter | 68 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-25 02:15
4073013 | 120-121-FE-008 | Repl Mech Hungry Boards OFF | 4073013 | 120-121 | Day | Fitter | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 12:15
4077532 | 120-121-FE-008 | 8W Mech OFF Insp Conv 121-FE-008 | 4077532 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 07:15
4084747 | 120-121-MA-003 | Mag 3 Blocked Line NDE | 4084747 | 120-121 | Day | Lube | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 12:15
4082938 | 120-121-MA-003 | Damaged Grease line NE side | 4082938 | 120-121 | Day | Fitter | 5 |  | 0 | Not Started |  |  |  |  | 2026-04-22 06:15 | 2026-04-22 11:15
4077488 | 120-121-CV-002 | 8W Mech OFF Insp Conv 121-CV-002 | 4077488 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 07:15 | 2026-04-22 08:15
4077493 | 120-121-CV-003 | 8W Mech OFF Insp Conv 121-CV-003 | 4077493 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 08:15 | 2026-04-22 09:15
4077489 | 120-121-CV-002 | 8W Mech OFF Insp Rollers 121-CV-002 | 4077489 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-22 09:15 | 2026-04-22 12:15
4077498 | 120-121-CV-004 | 8W Mech OFF Insp Conv 121-CV-004 | 4077498 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 09:15 | 2026-04-22 10:15
4077503 | 120-121-CV-005 | 8W Mech OFF Insp Conv 121-CV-005 | 4077503 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 10:15 | 2026-04-22 11:15
4077508 | 120-121-CV-006 | 8W Mech OFF Insp Conv 121-CV-006 | 4077508 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 11:15 | 2026-04-22 12:15
4078377 | 120-121-CV-003 | Replace Impact rollers 121-CV-003 | 4078377 | 120-121 | Day | Roller Crew | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-22 12:15 | 2026-04-22 18:15
4077528 | 120-121-CV-024 | 8W Mech OFF Insp Conv 121-CV-024 | 4077528 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-22 12:15 | 2026-04-22 13:15
4077491 | 120-121-CV-002 | 8W Mech OFF Insp Skirts 121-CV-002 | 4077491 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-22 14:15 | 2026-04-22 22:15
4077496 | 120-121-CV-003 | 8W Mech OFF Insp Skirts 121-CV-003 | 4077496 | 120-121 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-22 22:15 | 2026-04-23 06:15
4077494 | 120-121-CV-003 | 8W Mech OFF Insp Rollers 121-CV-003 | 4077494 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-23 06:15 | 2026-04-23 09:15
4077501 | 120-121-CV-004 | 8W Mech OFF Insp Skirts 121-CV-004 | 4077501 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-23 06:15 | 2026-04-23 14:15
4075579 | 120-121-FE-002 | Repl Mech Feeder Pan OFF | 4075579 | 120-121 | Day | Fitter | 24 |  | 0 | Not Started |  |  |  |  | 2026-04-23 06:15 | 2026-04-24 06:15
4078451 | 120-121-CV-004 | Change Impact Rollers | 4078451 | 120-121 | Day | Roller Crew | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-23 09:15 | 2026-04-23 15:15
4072480 | 120-121-FE-008 | Raise hard Skirts | 4072480 | 120-121 | Day | Fitter | 92.8 |  | 0 | Not Started |  |  |  |  | 2026-04-23 10:15 | 2026-04-27 07:00
4077506 | 120-121-CV-005 | 8W Mech OFF Insp Skirts 121-CV-005 | 4077506 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-23 14:15 | 2026-04-23 22:15
4077499 | 120-121-CV-004 | 8W Mech OFF Insp Rollers 121-CV-004 | 4077499 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-23 15:15 | 2026-04-23 18:15
4077511 | 120-121-CV-006 | 8W Mech OFF Insp Skirts 121-CV-006 | 4077511 | 120-121 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-23 22:15 | 2026-04-24 06:15
4079923 | 120-121-BN-004 | BN-004 Replace Lower Liners | 4079923 | 120-121 | Day | Boilermaker | 71 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:00 | 2026-04-27 05:00
4082141 | 120-121-CH-039 | CH-039 Replace Liners | 4082141 | 120-121 | Day | Fitter | 20 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:00 | 2026-04-25 02:00
4071393 | 120-122 | 12W Mech OFF Svce Lube DMS | 4071393 | 120-122 | Day | Lube | 25 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:00 | 2026-04-25 07:00
4078068 | 120-125-FL-008 | FL-008 Shim Belt Support Roller Frames | 4078068 | 120-125 | Day | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:00 | 2026-04-24 14:00
4078070 | 120-125-FL-008 | FL-008 Repair Discharge Scraper Frame | 4078070 | 120-125 | Day | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:00 | 2026-04-24 15:00
4077504 | 120-121-CV-005 | 8W Mech OFF Insp Rollers 121-CV-005 | 4077504 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:15 | 2026-04-24 09:15
4077535 | 120-121-FE-008 | 8W Mech OFF Insp Skirts 121-FE-008 | 4077535 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 06:15 | 2026-04-24 14:15
4074307 | 120-121-CR-004 | 121-DV-001 Replace Cooling Fan | 4074307 | 120-121 | Day | Fitter | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 12:00
4070776 | 120-122-PP-022 | PP-022 Replace Valve Seal Kit | 4070776 | 120-122 | Day | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 17:00
4075282 | 120-122-PP-044 | PP-044 Replace Valve | 4075282 | 120-122 | Day | Fitter | 5.5 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 13:30
4070824 | 120-122-PP-253 | PP-253 Replace Valve Seal Kit | 4070824 | 120-122 | Day | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 15:00
4083091 | 120-122-SC-017 | SC-017 Replace Underflow Spool | 4083091 | 120-122 | Day | Fitter | 18 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-25 02:00
4077572 | 120-122-ST-001 | 8W Mech OFF Insp Conv 122-ST-001 | 4077572 | 120-122 | Day | Conveyor | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 09:00
4077575 | 120-122-ST-001 | 8W Mech OFF Insp Skirts 122-ST-001 | 4077575 | 120-122 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 16:00
4077756 | 120-122-ST-001 | ST-001 Change Conveyor Gearbox Oil | 4077756 | 120-122 | Day | Lube | 3.5 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 11:30
4077577 | 120-122-ST-002 | 8W Mech OFF Insp Conv 122-ST-002 | 4077577 | 120-122 | Day | Conveyor | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 09:00
4085017 | 120-123-PP-063 | BI - Replace Suction & Discharge Valves | 4085017 | 120-123 | Day | Fitter | 2 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 10:00
4059002 | 120-123-SA-004 | SA-004 Replace Sampler | 4059002 | 120-123 | Day | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 08:00 | 2026-04-24 16:00
4077509 | 120-121-CV-006 | 8W Mech OFF Insp Rollers 121-CV-006 | 4077509 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-24 09:15 | 2026-04-24 12:15
4082032 | 120-121-CH-032 | CH-032 Replace Liners | 4082032 | 120-121 | Day | Boilermaker | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-24 22:00
4077513 | 120-121-CV-010 | 8W Mech OFF Insp Conv 121-CV-010 | 4077513 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-24 11:00
4076131 | 120-122-BW-007 | BW-007 Replace Weightometer Roller | 4076131 | 120-122 | Day | Trade Assistant | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-24 14:00
4078780 | 120-122-CV-013 | CV-013 Replace Bend Pulleys | 4078780 | 120-122 | Day | Fitter | 31 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-25 17:00
4068240 | 120-122-CV-014 | Replace Grease lines Bends & T/U | 4068240 | 120-122 | Day | Lube | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-24 18:00
4068113 | 120-122-CV-021 | CV-021 Soft Skirts Need Lowering | 4068113 | 120-122 | Day | Conveyor | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-24 14:00
4075585 | 120-122-CY-005 | Repl Mech Cyclone OFF | 4075585 | 120-122 | Day | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-24 22:00
4079910 | 120-123-ML-001 | 12W Mech OFF 3D Scan Mill 123-ML-001 Pre | 4079910 | 120-123 | Day | Fitter | 79 |  | 0 | Not Started |  |  |  |  | 2026-04-24 10:00 | 2026-04-27 17:00
4077518 | 120-121-CV-011 | 8W Mech OFF Insp Conv 121-CV-011 | 4077518 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 11:00 | 2026-04-24 12:00
4077523 | 120-121-CV-012 | 8W Mech OFF Insp Conv 121-CV-012 | 4077523 | 120-121 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 12:00 | 2026-04-24 13:00
4077529 | 120-121-CV-024 | 8W Mech OFF Insp Rollers 121-CV-024 | 4077529 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-24 12:15 | 2026-04-24 15:15
4077537 | 120-122-CV-013 | 8W Mech OFF Insp Conv 122-CV-013 | 4077537 | 120-122 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 13:00 | 2026-04-24 14:00
4075597 | 120-122-PP-044 | 12W Mech OFF Repl Pump 122-PP-044 | 4075597 | 120-122 | Day | Fitter | 17 |  | 0 | Not Started |  |  |  |  | 2026-04-24 13:30 | 2026-04-25 06:30
4076210 | 120-122-BW-009 | BW-009 Replace Weightometer Roller | 4076210 | 120-122 | Day | Trade Assistant | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:00 | 2026-04-24 18:00
4077542 | 120-122-CV-014 | 8W Mech OFF Insp Conv 122-CV-014 | 4077542 | 120-122 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:00 | 2026-04-24 15:00
4077516 | 120-121-CV-010 | 8W Mech OFF Insp Skirts 121-CV-010 | 4077516 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:15 | 2026-04-24 22:15
4075603 | 120-124 | 12W Mech OFF Svce Lube MS & Flot | 4075603 | 120-124 | Day | Lube | 11.5 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:30 | 2026-04-25 02:00
4070645 | 120-124-AG-001 | Replace Agitator blades | 4070645 | 120-124 | Day | Fitter | 17 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:30 | 2026-04-25 07:30
4069166 | 120-124-PP-080 | PP-080 Changeout Spools at Flowmeter | 4069166 | 120-124 | Day | Fitter | 33 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:30 | 2026-04-25 23:30
4085530 | 120-124-PP-124 | BI-Replace Discharge valve | 4085530 | 120-124 | Day | Fitter | 11 |  | 0 | Not Started |  |  |  |  | 2026-04-24 14:30 | 2026-04-25 01:30
4077547 | 120-122-CV-015 | 8W Mech OFF Insp Conv 122-CV-015 | 4077547 | 120-122 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 15:00 | 2026-04-24 16:00
4070823 | 120-122-PP-254 | PP-254 Replace Valve Seal Kit | 4070823 | 120-122 | Day | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 15:00 | 2026-04-24 23:00
4077533 | 120-121-FE-008 | 8W Mech OFF Insp Rollers 121-FE-008 | 4077533 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-24 15:15 | 2026-04-24 18:15
4071742 | 120-126-PP-158 | PP-158 Replace Valve Seal Kit | 4071742 | 120-126 | Day | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-24 15:30 | 2026-04-24 22:30
4077552 | 120-122-CV-018 | 8W Mech OFF Insp Conv 122-CV-018 | 4077552 | 120-122 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 16:00 | 2026-04-24 17:00
4077580 | 120-122-ST-002 | 8W Mech OFF Insp Skirts 122-ST-002 | 4077580 | 120-122 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 16:00 | 2026-04-25
4077557 | 120-122-CV-019 | 8W Mech OFF Insp Conv 122-CV-019 | 4077557 | 120-122 | Day | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 17:00 | 2026-04-24 18:00
4068199 | 120-122-CV-015 | Replace Grease lines, Bends & T/U | 4068199 | 120-122 | Night | Lube | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 18:00 | 2026-04-25 02:00
4077562 | 120-122-CV-020 | 8W Mech OFF Insp Conv 122-CV-020 | 4077562 | 120-122 | Night | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 18:00 | 2026-04-24 19:00
4070775 | 120-122-PP-023 | PP-023 Replace Valve Seal Kit | 4070775 | 120-122 | Night | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-24 18:00 | 2026-04-25 03:00
4055066 | 120-122-PP-038 | PP-038 Replace Scuttle Valve | 4055066 | 120-122 | Night | Fitter | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-24 18:00 | 2026-04-25
4077567 | 120-122-CV-021 | 8W Mech OFF Insp Conv 122-CV-021 | 4077567 | 120-122 | Night | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 19:00 | 2026-04-24 20:00
4077582 | 120-123-CV-022 | 8W Mech OFF Insp Conv 123-CV-022 | 4077582 | 120-123 | Night | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-24 20:00 | 2026-04-24 21:00
4077585 | 120-123-CV-022 | 8W Mech OFF Insp Skirts 123-CV-022 | 4077585 | 120-123 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 21:00 | 2026-04-25 05:00
4075586 | 120-122-CY-006 | Repl Mech Cyclone OFF | 4075586 | 120-122 | Night | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-24 22:00 | 2026-04-25 10:00
4076543 | 120-124-CY-024 | XV-4467 Replace Valve or Seal | 4076543 | 120-124 | Night | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 22:00 | 2026-04-25 06:00
4077521 | 120-121-CV-011 | 8W Mech OFF Insp Skirts 121-CV-011 | 4077521 | 120-121 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-24 22:15 | 2026-04-25 06:15
4063271 | 120-126-PP-162 | 126-XV-7629 Replace Valve | 4063271 | 120-126 | Night | Fitter | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-24 22:30 | 2026-04-25 04:30
4083066 | 120-122-PP-254 | PP-254 Replace Drain Valve | 4083066 | 120-122 | Night | Fitter | 4.5 |  | 0 | Not Started |  |  |  |  | 2026-04-24 23:00 | 2026-04-25 03:30
4074309 | 120-122-ST-002 | ST-002 Adjust Soft Skirts | 4074309 | 120-122 | Night | Conveyor | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-25 | 2026-04-25 03:00
4077862 | 120-122-CV-019-DRIV | JHA and Permit | 4077862 | 120-122 | Night | Lube | 5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 02:00 | 2026-04-25 07:00
4078341 | 120-122-HP-050 | HP-050 fines cyclone overflow feed box | 4078341 | 120-122 | Night | Fitter | 32 |  | 0 | Not Started |  |  |  |  | 2026-04-25 02:00 | 2026-04-26 10:00
4071386 | 120-121-FE-005 | Repl Mech Feeder Pan OFF | 4071386 | 120-121 | Night | Fitter | 24 |  | 0 | Not Started |  |  |  |  | 2026-04-25 02:15 | 2026-04-26 02:15
4077590 | 120-125-CV-023 | 8W Mech OFF Insp Skirts 125-CV-023 | 4077590 | 120-125 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-25 03:00 | 2026-04-25 11:00
4070777 | 120-122-PP-255 | PP-255 Replace Valve Seal Kit | 4070777 | 120-122 | Night | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-25 03:30 | 2026-04-25 12:30
4083081 | 120-122-PP-025 | Hole in suction spool | 4083081 | 120-122 | Night | Fitter | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-25 04:00 | 2026-04-25 10:00
4077587 | 120-125-CV-023 | 8W Mech OFF Insp Conv 125-CV-023 | 4077587 | 120-125 | Night | Inspector | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-25 05:00 | 2026-04-25 06:00
4076350 | 120-124-FC-028 | FC-028 Repl Drain Valv on HydrofloatCell | 4076350 | 120-124 | Day | Fitter | 4.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 06:00 | 2026-04-25 10:30
4077514 | 120-121-CV-010 | 8W Mech OFF Insp Rollers 121-CV-010 | 4077514 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-25 06:15 | 2026-04-25 09:15
4077526 | 120-121-CV-012 | 8W Mech OFF Insp Skirts 121-CV-012 | 4077526 | 120-121 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-25 06:15 | 2026-04-25 14:15
4070675 | 120-122-SC-021 | SC-021 C/O NDE Exciter Oil | 4070675 | 120-122 | Day | Lube | 2 |  | 0 | Not Started |  |  |  |  | 2026-04-25 07:00 | 2026-04-25 09:00
4074869 | 120-123-LU-004 | Insp Mech Mill Lube OFF | 4074869 | 120-123 | Day | Lube | 2.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 07:00 | 2026-04-25 09:30
4077519 | 120-121-CV-011 | 8W Mech OFF Insp Rollers 121-CV-011 | 4077519 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-25 09:15 | 2026-04-25 12:15
4074870 | 120-123-LU-007 | Insp Mech Mill Lube OFF | 4074870 | 120-123 | Day | Lube | 2.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 09:30 | 2026-04-25 12:00
4075587 | 120-122-CY-007 | Repl Mech Cyclone OFF | 4075587 | 120-122 | Day | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-25 10:00 | 2026-04-25 22:00
4076227 | 120-122-PP-025 | PP-025 Install Repaired Pipe Spool | 4076227 | 120-122 | Day | Fitter | 5.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 10:00 | 2026-04-25 15:30
4064387 | 120-124-PP-069 | JHA and Permit | 4064387 | 120-124 | Day | Fitter | 5.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 10:30 | 2026-04-25 16:00
4075598 | 120-123 | 24W Mech OFF Svce Lube Grin&Clas | 4075598 | 120-123 | Day | Lube | 0.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 12:00 | 2026-04-25 12:30
4071402 | 120-123-ML-001 | 6W Mech OFF Insp Lube Grin&Clas | 4071402 | 120-123 | Day | Lube | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-25 12:00 | 2026-04-25 15:00
4077524 | 120-121-CV-012 | 8W Mech OFF Insp Rollers 121-CV-012 | 4077524 | 120-121 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-25 12:15 | 2026-04-25 15:15
4077540 | 120-122-CV-013 | 8W Mech OFF Insp Skirts 122-CV-013 | 4077540 | 120-122 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-25 12:15 | 2026-04-25 20:15
4083195 | 120-122-PP-255 | replace drain valve MV-291 | 4083195 | 120-122 | Day | Fitter | 4.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 13:30 | 2026-04-25 18:00
4079565 | 120-123-CV-022-DRIV | Inform OPS for Isolations | 4079565 | 120-123 | Day | Lube | 3.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 15:00 | 2026-04-25 18:30
4077538 | 120-122-CV-013 | 8W Mech OFF Insp Rollers 122-CV-013 | 4077538 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-25 15:15 | 2026-04-25 18:15
4071743 | 120-122-PP-033 | PP-033 Replace Valve Seal Kit | 4071743 | 120-122 | Day | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-25 15:30 | 2026-04-25 22:30
4083099 | 120-124-PP-073 | PP-073 Replace Leaking Valve | 4083099 | 120-124 | Day | Fitter | 9.5 |  | 0 | Not Started |  |  |  |  | 2026-04-25 16:00 | 2026-04-26 01:30
4072027 | 120-122-PP-049 | 12W Mech OFF Repl Pump PP049 | 4072027 | 120-122 | Day | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-25 17:00 | 2026-04-26 06:00
4083382 | 120-124-SN-007 | SN-007 Install Permalube - Ring DRV | 4083382 | 120-124 | Night | Lube | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-25 18:30 | 2026-04-26 03:30
4063651 | 120-124-AG-003 | Review JHA, SWI & Lock On | 4063651 | 120-124 | Night | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-25 19:30 | 2026-04-26 08:30
4049198 | 120-124-PP-258 | PP-258 Replace Discharge Pipework | 4049198 | 120-124 | Night | Fitter | 10 |  | 0 | Not Started |  |  |  |  | 2026-04-25 20:00 | 2026-04-26 06:00
4076600 | 120-125-FL-008 | FL-008 Repair Feed Distributor Rubber | 4076600 | 120-125 | Night | Fitter | 18 |  | 0 | Not Started |  |  |  |  | 2026-04-25 20:00 | 2026-04-26 14:00
4077545 | 120-122-CV-014 | 8W Mech OFF Insp Skirts 122-CV-014 | 4077545 | 120-122 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-25 20:15 | 2026-04-26 04:15
4075588 | 120-122-CY-008 | Repl Mech Cyclone OFF | 4075588 | 120-122 | Night | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-25 22:00 | 2026-04-26 10:00
4078480 | 120-122-FE-011 | Parent Metal Repair and Reline FE011 | 4078480 | 120-122 | Night | Trade Assistant | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-25 22:00 | 2026-04-26 04:00
4071395 | 120-122-PP-036 | 12W Mech OFF Svce Cent Pump PP036 | 4071395 | 120-122 | Night | Fitter | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-25 22:30 | 2026-04-26 02:30
4070772 | 120-124-PP-104 | PP-104 Replace Valve | 4070772 | 120-124 | Night | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-25 23:30 | 2026-04-26 07:30
4070646 | 120-124-AG-004 | Review JHA, SWI & Lock On | 4070646 | 120-124 | Night | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-26 01:30 | 2026-04-26 14:30
4083222 | 120-124-PP-074 | PP-074 Replace Leaking Valve | 4083222 | 120-124 | Night | Fitter | 9.5 |  | 0 | Not Started |  |  |  |  | 2026-04-26 01:30 | 2026-04-26 11:00
4071387 | 120-121-FE-006 | Repl Mech Feeder Pan OFF | 4071387 | 120-121 | Night | Fitter | 24 |  | 0 | Not Started |  |  |  |  | 2026-04-26 02:15 | 2026-04-27 02:15
4067747 | 120-122-PP-037 | 24W Mech OFF C/O Pump PP037 | 4067747 | 120-122 | Night | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-26 02:30 | 2026-04-26 10:30
4083383 | 120-124-SN-008 | SN-008 Install Permalube - Ring DRV | 4083383 | 120-124 | Night | Lube | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-26 03:30 | 2026-04-26 12:30
4077550 | 120-122-CV-015 | 8W Mech OFF Insp Skirts 122-CV-015 | 4077550 | 120-122 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-26 04:15 | 2026-04-26 12:15
4075594 | 120-122-PP-041 | 12W Mech OFF Repl Pump 122-PP-041 | 4075594 | 120-122 | Day | Fitter | 6 |  | 0 | Not Started |  |  |  |  | 2026-04-26 06:00 | 2026-04-26 12:00
4071400 | 120-122-PP-050 | 12W Mech OFF Repl Pump PP050 | 4071400 | 120-122 | Day | Fitter | 17 |  | 0 | Not Started |  |  |  |  | 2026-04-26 06:00 | 2026-04-26 23:00
4063759 | 120-122-SC-015 | SC-015 Replace Motor | 4063759 | 120-122 | Day | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-26 06:00 | 2026-04-26 13:00
4073829 | 120-124-SA-044 | SA-044 Replace Sampler Spool | 4073829 | 120-124 | Day | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-26 06:00 | 2026-04-26 19:00
4077543 | 120-122-CV-014 | 8W Mech OFF Insp Rollers 122-CV-014 | 4077543 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-26 06:15 | 2026-04-26 09:15
4077873 | 120-126-PP-144 | PP-144 Replace Leaking Valve | 4077873 | 120-126 | Day | Fitter | 7.5 |  | 0 | Not Started |  |  |  |  | 2026-04-26 07:30 | 2026-04-26 15:00
4077548 | 120-122-CV-015 | 8W Mech OFF Insp Rollers 122-CV-015 | 4077548 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-26 09:15 | 2026-04-26 12:15
4075589 | 120-122-CY-013 | Repl Mech Cyclone OFF | 4075589 | 120-122 | Day | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-26 10:00 | 2026-04-26 22:00
4075595 | 120-122-PP-042 | 12W Mech OFF Repl Pump 122-PP-042 | 4075595 | 120-122 | Day | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-26 10:30 | 2026-04-26 23:30
4082027 | 120-121-CH-029 | CH-029 Replace Liners | 4082027 | 120-121 | Day | Boilermaker | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-26 11:00 | 2026-04-27
4072221 | 120-124-PP-075 | XV-4443 Replace Suction Valve | 4072221 | 120-124 | Day | Fitter | 10 |  | 0 | Not Started |  |  |  |  | 2026-04-26 11:00 | 2026-04-26 21:00
4077553 | 120-122-CV-018 | 8W Mech OFF Insp Rollers 122-CV-018 | 4077553 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-26 12:15 | 2026-04-26 15:15
4074310 | 120-122-CV-018 | Replace Soft skirts | 4074310 | 120-122 | Day | Conveyor | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-26 12:15 | 2026-04-27 00:15
4075605 | 120-125 | 12W Mech OFF Svce Lube Conc Filt | 4075605 | 120-125 | Day | Lube | 2.5 |  | 0 | Not Started |  |  |  |  | 2026-04-26 12:30 | 2026-04-26 15:00
4072489 | 120-126-TH-002 | 24W Mech OFF Insp Thick 126-TH-002 | 4072489 | 120-126 | Day | Fitter | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-26 14:00 | 2026-04-26 15:00
4077555 | 120-122-CV-018 | 8W Mech OFF Insp Skirts 122-CV-018 | 4077555 | 120-122 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-26 14:15 | 2026-04-26 22:15
4081126 | 120-125 | 12W Lube OFF Insp Oil Smpl Conc Filt | 4081126 | 120-125 | Day | Lube | 2 |  | 0 | Not Started |  |  |  |  | 2026-04-26 15:00 | 2026-04-26 17:00
4083365 | 120-125-CV-023 | CV-023 Gearbox oil C/O | 4083365 | 120-125 | Day | Lube | 4.5 |  | 0 | Not Started |  |  |  |  | 2026-04-26 15:00 | 2026-04-26 19:30
4072987 | 120-126-TH-003 | 48W Mech OFF Insp Thick 126-TH-003 | 4072987 | 120-126 | Day | Fitter | 6.5 |  | 0 | Not Started |  |  |  |  | 2026-04-26 15:00 | 2026-04-26 21:30
4077558 | 120-122-CV-019 | 8W Mech OFF Insp Rollers 122-CV-019 | 4077558 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-26 15:15 | 2026-04-26 18:15
4063654 | 120-124-AG-005 | Review JHA, SWI & Lock On | 4063654 | 120-124 | Day | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-26 16:30 | 2026-04-26 23:30
4071744 | 120-122-PP-039 | PP-039 Replace Valve Seal Kit | 4071744 | 120-122 | Night | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-26 19:30 | 2026-04-27 02:30
4075613 | 120-126 | 12W Mech OFF Svce Lube Tails | 4075613 | 120-126 | Night | Lube | 2 |  | 0 | Not Started |  |  |  |  | 2026-04-26 19:30 | 2026-04-26 21:30
4070774 | 120-124-PP-077 | PP-077 Replace Valve Seal Kit | 4070774 | 120-124 | Night | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-26 21:00 | 2026-04-27 06:00
4075590 | 120-122-CY-014 | Repl Mech Cyclone OFF | 4075590 | 120-122 | Night | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-26 22:00 | 2026-04-27 10:00
4071401 | 120-122-PP-051 | 12W Mech OFF Repl Pump PP051 | 4071401 | 120-122 | Night | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-26 23:00 | 2026-04-27 12:00
4075596 | 120-122-PP-043 | 12W Mech OFF Repl Pump 122-PP-043 | 4075596 | 120-122 | Night | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-26 23:30 | 2026-04-27 12:30
4077560 | 120-122-CV-019 | 8W Mech OFF Insp Skirts 122-CV-019 | 4077560 | 120-122 | Night | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-27 00:15 | 2026-04-27 08:15
4077595 | 120-122-SC-016 | Unbolt T-Piece Flange To Access Insert | 4077595 | 120-122 | Night | Fitter | 2.5 |  | 0 | Not Started |  |  |  |  | 2026-04-27 00:15 | 2026-04-27 02:45
4063655 | 120-124-AG-006 | Review JHA, SWI & Lock On | 4063655 | 120-124 | Night | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-27 01:30 | 2026-04-27 08:30
4071388 | 120-121-FE-007 | Repl Mech Feeder Pan OFF | 4071388 | 120-121 | Night | Fitter | 24 |  | 0 | Not Started |  |  |  |  | 2026-04-27 02:15 | 2026-04-28 02:15
4075263 | 120-122-PP-039 | 48W Mech OFF Repl Pump PP039 | 4075263 | 120-122 | Night | Fitter | 13 |  | 0 | Not Started |  |  |  |  | 2026-04-27 02:30 | 2026-04-27 15:30
4077596 | 120-122-SC-020 | Unbolt T-Piece Flange To Access Insert | 4077596 | 120-122 | Night | Fitter | 2.5 |  | 0 | Not Started |  |  |  |  | 2026-04-27 02:45 | 2026-04-27 05:15
4077597 | 120-122-SC-021 | Unbolt T-Piece Flange To Access Insert | 4077597 | 120-122 | Night | Fitter | 2.5 |  | 0 | Not Started |  |  |  |  | 2026-04-27 05:15 | 2026-04-27 07:45
4072294 | 120-124-PP-079 | XV-5004 Replace Discharge Valve Seals | 4072294 | 120-124 | Day | Fitter | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-27 06:00 | 2026-04-27 14:00
4077563 | 120-122-CV-020 | 8W Mech OFF Insp Rollers 122-CV-020 | 4077563 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-27 06:15 | 2026-04-27 09:15
4076545 | 120-124-PP-088 | PP-088 Replace Gland Water Valve | 4076545 | 120-124 | Day | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-27 07:45 | 2026-04-27 14:45
4077565 | 120-122-CV-020 | 8W Mech OFF Insp Skirts 122-CV-020 | 4077565 | 120-122 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-27 08:15 | 2026-04-27 16:15
4063656 | 120-124-AG-018 | Review JHA, SWI & Lock On | 4063656 | 120-124 | Day | Fitter | 19 |  | 0 | Not Started |  |  |  |  | 2026-04-27 08:30 | 2026-04-28 03:30
4077568 | 120-122-CV-021 | 8W Mech OFF Insp Rollers 122-CV-021 | 4077568 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-27 09:15 | 2026-04-27 12:15
4075591 | 120-122-CY-015 | Repl Mech Cyclone OFF | 4075591 | 120-122 | Day | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-27 10:00 | 2026-04-27 22:00
4083897 | 120-122-CV-021 | BI - REPLACE IMPACT ROLLERS | 4083897 | 120-122 | Day | Roller Crew | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-27 12:15 | 2026-04-27 16:15
4078466 | 120-122-PP-051 | XV-3350 suction valve need replacing | 4078466 | 120-122 | Day | Fitter | 5 |  | 0 | Not Started |  |  |  |  | 2026-04-27 13:00 | 2026-04-27 18:00
4077570 | 120-122-CV-021 | 8W Mech OFF Insp Skirts 122-CV-021 | 4077570 | 120-122 | Day | Conveyor | 8 |  | 0 | Not Started |  |  |  |  | 2026-04-27 14:15 | 2026-04-27 22:15
4070434 | 120-125-HU-006 | Insp Mech Thick HPU OFF | 4070434 | 120-125 | Day | Fitter | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-27 14:45 | 2026-04-27 15:45
4070433 | 120-125-XM-016 | 48W Mech OFF Insp Tripper 125-XM-016 | 4070433 | 120-125 | Day | Fitter | 4 |  | 0 | Not Started |  |  |  |  | 2026-04-27 15:45 | 2026-04-27 19:45
4077573 | 120-122-ST-001 | 8W Mech OFF Insp Rollers 122-ST-001 | 4077573 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-27 16:15 | 2026-04-27 19:15
4083380 | 120-124-PP-080 | PP-080 Replace Hose | 4083380 | 120-124 | Day | Fitter | 10 |  | 0 | Not Started |  |  |  |  | 2026-04-27 17:00 | 2026-04-28 03:00
4070778 | 120-122-PP-252 | PP-252 Replace Valve Seal Kit | 4070778 | 120-122 | Night | Fitter | 7 |  | 0 | Not Started |  |  |  |  | 2026-04-27 18:00 | 2026-04-28 01:00
4075592 | 120-122-CY-016 | Repl Mech Cyclone OFF | 4075592 | 120-122 | Night | Fitter | 12 |  | 0 | Not Started |  |  |  |  | 2026-04-27 22:00 | 2026-04-28 10:00
4074887 | 120-126-HU-007 | Insp Mech Thick HPU OFF | 4074887 | 120-126 | Night | Fitter | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-27 23:15 | 2026-04-28 00:15
4083363 | 120-124-PP-125 | HP-40 Clear Blockage | 4083363 | 120-124 | Night | Fitter | 5 |  | 0 | Not Started |  |  |  |  | 2026-04-28 | 2026-04-28 05:00
4074888 | 120-126-HU-008 | Insp Mech Thick HPU OFF | 4074888 | 120-126 | Night | Fitter | 1 |  | 0 | Not Started |  |  |  |  | 2026-04-28 00:15 | 2026-04-28 01:15
4046952 | 120-126-TH-003 | TH-003 RESET GUIDE SHIMS | 4046952 | 120-126 | Night | Fitter | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-28 01:15 | 2026-04-28 04:15
4054181 | 120-124-SA-020 | SA-020 Saunders Valve Cant Be Shut | 4054181 | 120-124 | Night | Fitter | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-28 03:00 | 2026-04-28 06:00
4070838 | 120-124-PP-086 | PP-086 Replace Valve Seal Kit | 4070838 | 120-124 | Night | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-28 03:30 | 2026-04-28 12:30
4070840 | 120-124-PP-067 | PP-067 Replace Valve Seal Kit | 4070840 | 120-124 | Night | Fitter | 9 |  | 0 | Not Started |  |  |  |  | 2026-04-28 04:15 | 2026-04-28 13:15
4077578 | 120-122-ST-002 | 8W Mech OFF Insp Rollers 122-ST-002 | 4077578 | 120-122 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-28 07:15 | 2026-04-28 10:15
4077583 | 120-123-CV-022 | 8W Mech OFF Insp Rollers 123-CV-022 | 4077583 | 120-123 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-28 10:15 | 2026-04-28 13:15
4077588 | 120-125-CV-023 | 8W Mech OFF Insp Rollers 125-CV-023 | 4077588 | 120-125 | Day | Roller Crew | 3 |  | 0 | Not Started |  |  |  |  | 2026-04-28 13:15 | 2026-04-28 16:15