## Manning
INTERNAL USE ONLY | [23 empty] | FLIGHT NUMBER |  | CONTRACTOR TO COMPLETE
[6 empty] | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | IN | OUT
PROCESSED | INX SHUTDOWN PROFILE NAME DO NOT TOUCH |  | COMPANY | LINE # DO NOT REMOVE | SKILLSET | 17.04.2026 | 18.04.2026 | 19.04.2026 | 20.04.2026 | 21.04.2026 | 22.04.2026 | 23.04.2026 | 24.04.2026 | 25.04.2026 | 26.04.2026 | 27.04.2026 | 28.04.2026 | 29.04.2026 | 30.04.2026 | 01.05.2026 | 02.05.2026 | 03.05.2026 | 04.05.2026 | EXPAND CELL FOR FLIGHT DETAILS | EXPAND CELL FOR FLIGHT DETAILS | SURNAME | GIVEN NAME Full Name NO Nicknames | SRG Contingent | LABOUR HIRE CONTINGENT |  | FFW DATE | DRIVERS LICENCE EXP DATE | WAH | CS | RG/DG | ForkLift | CN | EWP | Permit Acceptor | DETAILS / COMMENTS
|  |  | SRG | 14 | Boilermaker |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | ATTACK | Ben |  | MESSENGER | Bryan
|  |  | SRG | 15 | Boilermaker | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | DS | DS | DS | FOP | [5 empty] | MENDY | Mathias |  | HILLMAN MEYNELLY | Brendan Julian
|  |  | SRG | 44 | BOILERMAKER | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | NAIRN | Aaron |  | HILLMAN | Brendan
|  |  | SRG | 45 | BOILERMAKER | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | ROBINSON | William
|  |  | SRG | 30 | Bus Driver |  |  |  | DIP | DS | DS | DS | DS | DS | DS | DS | DS | DS | DOP | [6 empty] | BRYCE | David |  | HABAIEB | Yacine
|  |  | SRG | 16 | Coded Welder | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOP | [8 empty] | RISCHIA | Mirko
|  | Extra Nightshift - Plant Run up | SRG | 31 | Coordinator |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | NS | NS | FOA | [6 empty] | SMITH | Anthony
|  |  | SRG | 22 | Electrician |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP | [7 empty] | MEDANOVIC | Teo
|  |  | SRG | 23 | Electrician |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP | [7 empty] | CHOPPING | Benjamin
|  |  | SRG | 24 | Electrician |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | NS | FOA | [7 empty] | MAHONEY | James
|  |  | SRG | 25 | Electrician |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | NS | FOA | [7 empty] | BRAND | Drew
|  | Pre Shut Crew | SRG | 5 | Fitter |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | GARDINER | Edward
|  | Pre Shut Crew | SRG | 6 | Fitter |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | GRAINGER-ROUSSEAU | Malcolm
|  | Post Shut Crew | SRG | 7 | Fitter |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | PHILLIPS | Russell
|  | Post Shut Crew | SRG | 8 | Fitter | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | DS | DS | DS | FOP | [5 empty] | JAMES | Darren
|  | Post Shut Crew | SRG | 9 | Fitter | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | DS | DS | DS | FOP | [5 empty] | GANGEMI | Jake |  | SMITH | Elliot
|  | Post Shut Crew | SRG | 10 | Fitter | Fri: FIA; Sat: DS; Sun: DS; Mon: DS | DS | DS | DS | FOP | [5 empty] | LI | Mao | Ben Friedauer | STONE | Brett
|  |  | SRG | 11 | Fitter | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOP | [8 empty] | BOULAHDID | Walid |  | LARBI | Hamza
|  |  | SRG | 12 | Fitter | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOP | [10 empty] | Mackauly Parker
|  |  | SRG | 13 | Fitter | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOP | [8 empty] | DORUGADE | Omkar
|  | Extra Nightshift - Plant Run up | SRG | 35 | Fitter | Fri: FIA; Sat: NS; Sun: NS; Mon: NS | NS | NS | FOA | [6 empty] | MUKUNGA | Herbert |  | CAPALDI | Charlie
|  | Extra Nightshift - Plant Run up | SRG | 36 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | NS | NS | FOA | [6 empty] | LOORTHSMAY | Selva
|  | Extra Nightshift - Plant Run up | SRG | 37 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | NS | NS | FOA | [6 empty] | SAMMITO | Alessio |  | BENNETT | Ronald
|  |  | SRG | 38 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | SINGH | Gurshwinder
|  |  | SRG | 39 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | SINGH | Kulvinder
|  |  | SRG | 40 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | MOHAMED | Abdikadir
|  |  | SRG | 41 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | ADAMS | Jaime
|  |  | SRG | 42 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | ANADIF | Omar |  | LANZA | Jac
|  |  | SRG | 43 | Fitter | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | SCHAAF | Clemens
|  | Inspections | SRG | 58 | Fitter - Conveyor Inspections / Skirt Adjustments | Wed: FIA; Thu: DS; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOA | [8 empty] | CHAVOT | Florian | Martin Illyes
|  | Inspections | SRG | 59 | Fitter - Conveyor Inspections / Skirt Adjustments | Wed: FIA; Thu: DS; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOA | [8 empty] | GRONENBERG | Timo
|  | Inspections | SRG | 61 | Fitter - Conveyor Inspections / Skirt Adjustments | Wed: FIA; Thu: NS; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | UY | Gerry
|  | Inspections | SRG | 62 | Fitter - Conveyor Inspections / Skirt Adjustments | Wed: FIA; Thu: NS; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | GUNN | Samuel
|  | Inspections | SRG | 60 | Fitter - Inspections | Wed: FIA; Thu: DS; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOA | [8 empty] | GUND | Amit
|  | Inspections | SRG | 63 | Fitter - Inspections | Wed: FIA; Thu: NS; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | MANDIZVIDA | Wisdom |  | LOUISA | Armand
|  |  | SRG | 26 | HSE |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [6 empty] | JEFFERY | Jacinta
|  |  | SRG | 27 | HSE |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | NS | FOA | [7 empty] | Te Nahu | Pare
|  | Lube Team 1 D/S Only | SRG | 50 | Lube Tech T/A | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOP | [8 empty] | DJAFFER | Sebastien
|  | Lube Team 2 | SRG | 51 | Lube Tech T/A | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | FOP | [8 empty] | MOKEDDEM | Mehdi
|  | Lube Team 2 | SRG | 52 | Lube Tech T/A | Wed: FIA; Thu: NS; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | Vasanthan | LAKSHMAN
|  | Post Shut Crew | SRG | 17 | Rigger Advanced |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | DACK | Joe
|  | Post Shut Crew | SRG | 18 | Rigger Advanced | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | DS | DS | DS | FOP | [5 empty] | ARBUCKLE | Nathan |  | CORBETT HOPLA | Rhys Sven
|  | Extra Nightshift - Plant Run up | SRG | 46 | Rigger Advanced | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | NS | NS | FOA | [6 empty] | TRUSLOVE | Ricky
|  |  | SRG | 47 | Rigger Advanced | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | KIM | Chaeyoon |  | KOHI | Patrick
|  | Roller Crew | SRG | 53 | Roller Crew Supervisor |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | MCLENNAN | Chris
|  | Roller Crew | SRG | 54 | Roller Tech |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | KARIKIS | Stefanos | Gary Caverzasio
|  | Roller Crew | SRG | 55 | Roller Tech |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | GARCIA | King | Alexis Labrie | KAMR | Osama
|  | Roller Crew | SRG | 56 | Roller Tech |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | LAROCK | Jeremy |  | GABOSE | Mohamed
|  | Roller Crew | SRG | 57 | Roller Tech |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | MARTINS | Henri |  | COMBO | Soidridine Saindou
|  |  | SRG | 1 | Superintendent |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | RILEY | Adam
|  | Pre/Post Shut Crew | SRG | 2 | Supervisor DS |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | NEWELL | Lewis
|  | Pre/Post Shut Crew | SRG | 3 | Supervisor DS |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | BURNS | Peter
|  | Pre Shut Crew | SRG | 4 | Supervisor DS |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP | [8 empty] | CHAUDHARY | Kapil
|  |  | SRG | 21 | Supervisor Elec |  |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | FOP
|  | Extra Nightshift - Plant Run up | SRG | 32 | Supervisor NS |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | NS | NS | FOA | [6 empty] | SULLIVAN | Mark
|  |  | SRG | 33 | Supervisor NS |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | FOA | [8 empty] | KIRKBY | Jordan
|  |  | SRG | 34 | Supervisor NS |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | FOA | [8 empty] | McCowat | Tsarina
|  | Post Shut Crew | SRG | 19 | T.A. (Sentry) | Thu: FIA; Fri: DS; Sat: DS; Sun: DS; Mon: DS | DS | DS | DS | FOP | [5 empty] | BENDANI | Mehdi |  | JORKE DIXON | Alexander Liam
|  | Post Shut - Must have LF VOC | SRG | 20 | T.A. (Sentry) |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | JONES | Madeline |  | ROBERTS | Jason
|  | Extra Nightshift - Plant Run up | SRG | 48 | T.A. (Sentry) | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | THOMPSON | William | VAATAINEN Julia | ANNAKIN | Kyle
|  | Extra Nightshift - Plant Run up | SRG | 49 | T.A. (Sentry) | Thu: FIA; Fri: NS; Sat: NS; Sun: NS; Mon: NS | FOA | [8 empty] | MONDESIR | Lea |  | AKKAOUI | Chaimae
|  | Pre/Post Shut Crew | SRG | 28 | T.A. Telehandler |  |  |  | FIA | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | FOP | [5 empty] | JOEN | Ellie
|  | Pre/Post Shut Crew | SRG | 29 | T.A. Telehandler |  |  |  |  | FIA | NS | NS | NS | NS | NS | NS | NS | NS | FOA | [6 empty] | COX | Shane |  | FERRIS | Lewis
Key:
Current SRG employee
Labour Hire
Josh to confirm
New SRG onboard
Note on M2: Jason Greenacre: Dry Plant Tooltime starts 0600
Note on O2: Jason Greenacre: Wet Plant tooltime starts 0600
Note on Q2: Dwight Pitcher: Dry plant tooltime finishes 0600
Note on S2: Dwight Pitcher: Wet plant tooltime finishes 0600
Note on N6: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N7: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on L13: Dwight Pitcher: Fly in AM straight to rooms for N/S
Note on L14: Dwight Pitcher: Fly in AM straight to rooms for N/S
Note on O24: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N25: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N26: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N27: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N28: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N29: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N30: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N31: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N32: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on M35: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on M36: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on M38: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on AC41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Who is this?
Note on N46: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N47: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N63: Jason Greenacre: Fly in AM straight to rooms for N/S
Note on N64: Jason Greenacre: Fly in AM straight to rooms for N/S

## Sheet1
Role | Flat DS | Flat NS
Superintendent | 90 | 96
Coordinator | 85 | 90
Mech Supervisor | 75 | 82
Mech Fitter | 64 | 72 | 250000
Boilermaker | 64 | 72
Coded Welder | 67 | 75 | 223000
Rigger - Basic | 56 | 62
Rigger - Inter | 57 | 63
Rigger - Adv | 58 | 64
Roller Tech | 58 | 63
Trade Assistant / Bus Driver / Tele | 50 | 55
Electrical Supervisor | 77 | 84
Electrician | 70 | 78
Lube Tech | 64 | 72
HSE advisor | 76 | 85
QA/QC - Inspector | 81 | 88